## Untitled
Step | Agent | Phase | Evidence already in Drive | Gap to close | Quality gate | Status
1 | Scope | Understanding | Pilot plant Echuca, Rod deadline, 20-22% Adbri margin target, tech stack | Success criteria / KPIs, risks, brief sign-off | Gate 1: Project Brief | TO DO (input pack in plan)
2 | Stakeholder Mapping | Understanding | Steven Eeles, Rod, Damian Cherry, 2 new coordinators, managers, Accounts, Technical, Adbri, Daryl (API approval) | RACI, owners of steps 2, 12, 16 | Gate 2: Power structure | TO DO
3 | Current Solution | Understanding | 16-step as-is swimlane v0.2, Coleambally workbook, Command QC + Reporting Services | Heuristic/priority matrix, invisible manual steps | Gate 3: Diagnosis and priorities | MOSTLY DONE - run to prioritise
4 | User Mindset | Understanding | Roles only (coordinators, Damian, Rod) | Personas, devices/context, adoption risks | Behavioral verification | TO DO
5 | Benchmark | Understanding | None | Quoting/pricing automation tools in concrete/construction | Competitive differentiation | TO DO (lower priority)
6 | Interview | Understanding | 8 Oct session, questionnaire | Steven-mediated P1 guide; Damian as 2nd source | Neutrality of questions | URGENT
7 | Run interviews (human) | Understanding |  | Complete before 31 Oct 2026 |  | URGENT
8 | Insights | Analysing |  | Needs interview answers; JTBD | Gate 4: JTBD and use cases | BLOCKED on step 7
9 | User Journey | Analysing | As-is swimlane as base | Pain points and improvements | Journey map precision | TO DO
10 | Use Cases | Analysing | Prototype screens imply some | Evidence-based list, error flows | Gate 4: JTBD and use cases | TO DO
11 | Envision | Envisioning |  | Value proposition | Gate 5: Value proposition | TO DO
12 | Storyteller | Envisioning |  | Pitch and scenarios | Gate 5: Presentation | TO DO
13 | Prompt to Prototype | Envisioning | Mawsons_Ops_Prototype.html (Dashboard, Quotes, Exception Reports, Plant Matrix, New Quote) | Re-spec from approved use cases | Gate 5: Prototype | PROTOTYPE v0 EXISTS