## Untitled
Section | Item | Detail | Assumed
Status | Gate 1 | Approved on assumptions (provisional)
Client | Company | Mawsons: ready-mix concrete and quarry business (regional VIC / southern NSW)
Client | Suppliers | Cement exclusively from ICL (Adbri-owned); aggregates and sands from own quarry; admixtures external
Problem | Core problem | Quote and pricing accuracy depends on Rod (retiring end Oct 2026; returns late Dec/Jan; avoids direct interviews; Steven is the conduit)
Problem | Rod's tacit checks | 3 morning exception reports; plant feasibility; second price check; quote expiry and price-increase tracking
Objective | Objective | Capture Rod's tacit knowledge and automate or de-risk the quote-to-cash pricing checks. Pilot plant: Echuca
Scope | In scope | 16-step workflow (price foundation, quote build, quote to cash); Command QC; Reporting Services; costing workbook
Scope | Out of scope | Replacing Command QC; non-pilot plants in release 1 | Yes
Users | Users | 2 new coordinators (Nov); Damian Cherry; plant/regional/ops managers; Rod in January
Success criteria | 1 | The 3 morning exception reports run automatically and match Rod's results on a sample | Yes
Success criteria | 2 | Mix designs auto-checked against a plant-capability matrix before the costing sheet is built (warn or block rule TBC) | Yes
Success criteria | 3 | Quote expiry (30-day) and supplier price-increase alerts are live with a named recipient and action | Yes
Success criteria | 4 | Every workflow step has a named owner from 1 Nov 2026 (steps 2, 12, 16 first) | Yes
Success criteria | 5 | Margin versus the 20-22% Adbri target is flagged on every quote | Yes
Priority | Order | 4 and 1 first (ownership gap, exception reports), then 2, 3, 5 | Yes
Timing | Timeline | Knowledge capture before 31 Oct; build and validation with Rod in Jan | Yes
Risk | R1 | Command QC API access unconfirmed (needs Daryl's approval)
Risk | R2 | Rod's knowledge loss; indirect access only
Risk | R3 | Costing tab stale (7 of 8 plants dated 1 Oct 2023)
Risk | R4 | No cartage formula, no margin formula, no quarry-to-concrete code map
Risk | R5 | Step 12 (accepted pricing into Command) owner unconfirmed (Rod, I think)
Open question | Q1 | Numeric targets (hours saved, errors avoided)? Not yet defined
Open question | Q2 | Replicate Rod's checks or redesign the process? Assumed: replicate first, redesign later | Yes
Open question | Q3 | Budget and post-October timeline?
Open question | Q4 | Command API approval status and who is chasing it?
Open question | Q5 | Who decides a mix is standard (skips design and costing)?